Review of the RELU Programme’s Seed-Corn Funding Mechanisms

CONTRACT REF:UNT/357

Report by

Laura R. Meagher, PhD

Technology Development Group

and

Catherine Lyall, PhD

Information Browser Ltd

16 February 2007

Contents

Executive Summary	1

1.	Introduction: Objectives, Methods	1

Objectives	1

Methods	1

2.	Value Added: Impacts of Catalytic, Seed-Corn Funding Mechanisms	1

Background information	1

Did the seed-corn mechanisms mobilise interest and engage researchers?	1

What sorts of activities helped to build interdisciplinarity, through what developmental stages?	1

Did the awards help to forge new linkages and/or strengthen existing ones?	1

What if any  effects of seed-corn funding persist?	1

Has expertise in interdisciplinary working grown?	1

Did awards encourage involvement of external stakeholders?	1

Have seed-corn awards opened up subsequent possibilities for participants?	1

3.	Lessons Learned & Messages for Future Schemes	1

Background Information	1

Mobilising a new research community	1

Building interdisciplinary research capacity between the natural and social sciences	1

Priority issues or obstacles encountered	1

Value-added	1

Other seed-corn programmes	1

Messages for future seed-corn funding schemes	1

4.	Conclusions	1

Summary of findings	1

Reviewers’ final comments	1

# Executive Summary

- This review focuses on the seed-corn funding mechanisms utilised by the UK Research Councils’ ESRC Rural Economy and Land Use programme (RELU) (Capacity Building Awards, Scoping Studies, Development Awards and Networking Awards). The key overarching objectives of the evaluation were: (1) To review how the seed corn funding mechanisms have contributed to the RELU programme and objectives and (2) To review how the awards have contributed to broader interdisciplinary capacity in this field. A Framework of Core Questions eliciting information toward these ends was designed to guide and integrate the several methodologies used: document analysis (end-of-award reports), survey of researchers (65 returned surveys), and semi-structured interviews (22 in addition to RELU leaders, including researchers, stakeholders, individuals with overview perspectives and senior figures in other interdisciplinary programmes).

- Overall, the Review found RELU’s seed-corn scheme to be effective in addressing its aims. The Review supports the nearly unanimous opinion of survey respondents and interviewees that seed-corn funding can play very important roles in catalysing interdisciplinarity and the building of interdisciplinary communities with increased capacity to tackle complex problems.

- The seed-corn awards mobilised interest in the RELU programme, engaging diverse researchers in its issues. Many researchers viewed the awards as opportunities to address their desire to conduct interdisciplinary work; in fact many were already involved in interdisciplinary work. In contributing to the programme’s aims, the scheme also contributed to broader interdisciplinary capacity in related fields, with seed-corn researchers in many cases increasing their commitment to and/or competence at interdisciplinary working.

- At various stages (pre-award, award, post-award), a variety of “linking” activities were facilitated by awards,  including informal links and networks between researchers, and between researchers and other stakeholders, cross-disciplinary meetings, visits/exchanges, cross-disciplinary interactions with stakeholders, interdisciplinary publications, subsequent bids to RELU and other funders, links within/between institutions and involvement in other cross-disciplinary initiatives.

- Hallmarks of the awards were the linkages between researchers and between disciplines that were forged or strengthened. Indeed, a great many researchers continue to be involved in interdisciplinary research spanning social and natural science, with an enhanced understanding of other disciplines. Some linkages with stakeholders and across institutions were forged or strengthened, with some continuing. Follow-on activity includes full-project bids to RELU, which in many cases appear to have been strengthened by seed-corn experience, and to other sources, although it is still too early to tell if success there has been affected.

- RELU’s funding mechanisms appear effective, in a general comparison with those used in several other interdisciplinary programmes. Some administrative aspects could have been improved, primarily the speed with which calls and awards were announced and, especially, the timing of calls for full proposals relative to very young seed-corn projects. Issues of assessment appropriate to interdisciplinary bids also arose.  Some other programmes appear to make a point of bringing together their seed-corn counterparts to share concerns and good practice as to processes involved; some may give their seed-corn projects a somewhat higher profile within their overarching initiative.

- While the different award types addressed slightly different aims, division of RELU’s seed-corn scheme into four funding mechanisms seemed unnecessary. It might be preferable to offer one more generalised, flexible scheme of seed-corn awards, which could be clearly defined to encompass the several types of nature/aim, instead of artificially “forcing” distinctions among different award streams.

- An important contribution of the scheme has been the enhancement of researchers’ ability to participate in other, future interdisciplinary collaborations. Lessons learned through the RELU seed-corn experience indicate that researchers conducting seed-corn projects can become more successful at building interdisciplinary skills and community, if they come to understand the processes involved in so doing. (Such processes are illustrated, for example, by this Review’s explication of the flow of activities dominating the various stages of bid-writing, conducting the award, post-award.)  Examples of overarching lessons learned about building interdisciplinary research capacity and mobilising new research communities include: length of time and degree of effort needed; the importance of prospects for follow-on activity and funding; the importance of clear, shared objectives; the need to understand necessary processes and steps; and the identification of a number of issues and challenges arising during interdisciplinary research.

- A number of lessons learned were offered as suggestions to funders or leaders of seed-corn schemes in future research programmes on complex topics. Some were analogous to messages to seed-corn project leaders, e.g. take the extra time needed to design and establish the scheme and capture and share lessons learned across funding bodies, as well as across researchers. Individuals were keenly aware of the importance of assessment issues, particularly the need to select or train assessors who can place appropriate value on proposals showing genuine interdisciplinarity.

- At a time when society looks to interdisciplinary research to tackle its complex problems, this practical learning thus represents a national resource to which the RELU seed-corn scheme has contributed. There is a general appetite for this sort of learning, such that sharing it could help to avoid reinvention of wheels and unnecessary problems in pursuing or funding seed-corn projects.  We hope that this Review of RELU’s seed-corn scheme will contribute to both these reservoirs of organisational learning.

# Introduction: Objectives, Methods

## Objectives

  - The key overarching objectives of the evaluation were:

- To review how the awards have contributed to the RELU programme and objectives

- To review how the awards have contributed to broader interdisciplinary capacity in this field

and the principal questions addressed by the review are detailed in Box 1.

To what extent were the awards successful in mobilising interest in the RELU programme from across the social, environmental and biosciences, and in bringing together these different research communities? Did the funding mechanisms enhance levels of interdisciplinary research capacity? If so, in what ways has this been realised during and after proposals/projects? Have the awards informed the broader development of the programme? If so how? What linkages were forged or strengthened between researchers, disciplines, institutions or with stakeholders? To what extent were these collaborations entirely new or did they build on existing links? Did the awards alter understanding of other disciplines and Research Councils and did they lead to more or less favourable attitudes towards collaboration across disciplines between the natural and social sciences? What subsequent activities were facilitated amongst applicants (joint-initiatives, publications, funding bids, research awards, institutionalised links, career progression of investigators and researchers and other forms of collaboration)? To what extent are the award holders and researchers engaged on projects still involved in inter-disciplinary research between the natural or social sciences and/or still in contact with new collaborators involved in the RELU project? Were there any other lasting effects? Did the awards strengthen the quality and integration of natural and social sciences in proposals for larger research projects in subsequent calls for funding? What lessons can be captured for building interdisciplinary capacity in the future, more generally? What were the overarching lessons that can be identified regarding the building of interdisciplinary research capacity between the natural and social sciences, and the mobilisation of a new research community (including the capacity building effects of the bidding process itself)? How might the funding mechanisms be enhanced in future if other research programmes were to apply them (including questions concerning scale and duration)? Which mechanisms were most successful and cost effective? How does RELU’s funding mechanisms compare with those used in other interdisciplinary programmes?

Box 1: Review Questions

## Methods

  - The reviewers captured the principal questions of the review and developed them into a Framework of Core Questions which underpinned all of the methodologies employed. This common framework enabled integration across methods to address the central aims of the review.

### Document Analysis

  - End-of-award Reports were analysed to identify useful examples, key points and practical lessons learned. Results were captured as:

- examples of roles played by seed corn grants

- examples of interdisciplinary groupings

- illustrative types of stakeholder involvement

- examples of interactions within RELU

- challenges faced by seed corn projects

- lessons learned regarding the promotion of interdisciplinarity

- lessons learned regarding the inclusion of stakeholders

- and other relevant points arising.

The document analysis thus provided important qualitative input from award-holders into the integrative Review and background information for the telephone interviews.

### Surveys

  - A four-page questionnaire comprising a mix of Lickert scale, pre-coded and free text response modes was designed in consultation with RELU staff (see Annex A) and elicited information relevant to the Framework of Core Questions.  An email contacts database for this evaluation was provided by the RELU office.  This database included all 34 award-holders (PIs), as well as co-investigators and others associated with the awards.  Once the database had been cleaned (duplicates removed, names omitted where no email address had been provided or where the address was no longer valid, etc.), this yielded a sample of 120 names.  Surveys were distributed electronically on 13 and 14 November 2006, two reminders were sent and the data collection was closed on 11 December.

| The overall response rate was 54% (65 completed surveys) with a 74% (25 out of 34) response rate from PIs. The breakdown of respondents was PI 38%, Co-I 46%, Research assistant 14%, Other 2%. |  |
| --- | --- |

  - Responses were entered into a database and histograms and percentage figures produced for each question (Annex B).  In addition, responses were analysed (i) by type of award, (ii) by role, (iii) by discipline, and (iv) by whether or not the respondent was still working in an interdisciplinary environment (Annex C).  Where any obvious differences were apparent between these different categories of response these are noted in the following commentary.

### Interviews

  - Semi-structured interviews were conducted, based upon the Framework of Core Questions. Coded interview transcripts were analysed to identify common themes and resulting conceptual clusters were utilised to inform and structure Section 3 of this Report. (In order to add a level of richness of understanding, and a flavour of the participants’ input, verbatim or near-verbatim quotations are on occasion captured in quotation marks in the report text.) Between 27 November and 19 December, twenty-two telephone interviews (in addition to discussion with RELU leadership) gathered input from a deliberate mix of perspectives. Some interviews were held with awardholders of different types of seed corn projects; some were held with stakeholders with an informed view of the scheme; some were held with individuals having an overview of the scheme; and some were held with directors or senior figures in other programmes oriented toward interdisciplinarity (e.g. government (primarily UK) funding schemes, centres or multi-node programmes) (Table 1).

| PIs | 7 |
| --- | --- |
| Stakeholders | 5 |
| Overview | 3 |
| Senior Figures re Other Programs | 7 |
| TOTAL Interviews | 22 (+RELU leadership) |

Table 1: Interviews conducted

### Analysis

  - Input from all three methods has been analysed and integrated into this review. Section 2 reports data from surveys (signalled by references to “respondents”), augmented by analysis of input from interviewees and from end-of-award reports. Section 3 on Lessons Learned and Recommendations draws primarily on insights elicited during interviews, augmented by free text responses to the survey.

# Value Added: Impacts of Catalytic, Seed-Corn Funding Mechanisms

## Background information

  - The RELU ‘seed-corn’ funding mechanisms were intended to mobilise interest in the programme across diverse research communities in the social, environmental and biosciences. The awards, made initially as part of the programme’s first funding call, aimed to facilitate the development of interdisciplinary research capacity and new interdisciplinary research collaborations between natural and social scientists, with a view, in part, to strengthening proposals for larger research projects in subsequent funding calls. Specific funding modes were also designed to encourage innovative higher risk/adventurous interdisciplinary research and to facilitate greater engagement of non-academic stakeholders.  The 34 awards (selected from 94 proposals) are listed in Annex E and comprised:

CAPACITY BUILDING AWARDS (5 awards from 14 proposals, 38% success rate)

Funds were available for awards focusing on any of the RELU themes, up to a maximum of £50k, to facilitate the development of interdisciplinary research capacity over a 12 month period.

SCOPING STUDIES (14 awards from 50 proposals, 28% success rate)

Funds were available for awards focusing on any of the RELU themes, up to a maximum of £50k. Applicants had to demonstrate the interdisciplinary nature of the proposed research. Awards could be up to 12 months in duration.

DEVELOPMENT ACTIVITY AWARDS (8 awards from 18 proposals, 44% success rate)

Awards of up to £20k were available for activities designed to facilitate the development of the RELU programme and/or demonstrate its value and potential.

NETWORKING AWARDS (7 awards from 12 proposals, 58% success rate)

Awards of up to £5k to facilitate the development of proposals under the second call, to fund consortium and travel and meeting costs.

## Did the seed-corn mechanisms mobilise interest and engage researchers?

  - In considering a key objective of the RELU programme, the review sought to assess the extent to which awards had been successful in mobilising interest in the RELU programme from across the social, environmental and biosciences and in bringing together these different research communities.

| Survey respondents identified themselves as coming mainly from the social sciences (46%) and the environmental sciences (38%) with only 3% from the biosciences. |  |
| --- | --- |

| The breakdown of awards held by respondents was Capacity Building (25%), Scoping Studies (55%), Development Activity (14%), Networking Award (14%). Proportionately more holders of Capacity Building and Scoping Studies awards took the effort to respond than were funded (18% and 41% of overall awards, respectively). |  |
| --- | --- |

| There was general agreement that the award had brought together researchers from the social and natural sciences (52% strongly agree; 38% agree) with the environmental scientists (ES) being slightly more positive than the social scientists (SS) (ES 68% strongly agree; SS 47% strongly agree). |  |
| --- | --- |

  - Interviewees contributed insights into how researchers were brought together from across social and natural sciences. Mixing of disciplines was quite motivating but researchers also recognised the challenges of bringing people together (see Section 3, lessons learned).

| The prospect of gaining an award stimulated interest and potential engagement amongst respondents regarding the RELU programme (43% strongly agree; 45% agree) although they were less certain as to whether the awards had stimulated other collaborators’ interest and potential engagement (25% strongly agree; 51% agree; 20% neutral). |  |
| --- | --- |

| Opinion was slightly more mixed on whether others (beyond the award-holders, researchers and stakeholders who might have been involved in the bidding process) had been drawn into the funded activities (26% strongly agree; 40% agree; 20% neutral; 12% disagree). (For some, but not all, of the seed-corn projects, additional stakeholders and/or researchers were involved as a deliberate part of the plan, e.g. through large workshops.) |  |
| --- | --- |

  - Interviewees generally agreed that the prospect of gaining even a seed-corn award stimulated interest and potential engagement, with some feeling that the opportunity addressed a long pent-up wish to do interdisciplinary work and/or to address a particular complex problem. (Of course, the potential of even more funding in the full project stage was motivational for some participants.) Many recognised that the degree to which seed-corn grants (as opposed to full project grants) could accomplish desired ends was of necessity limited, since processes of genuine integration take time. In this regard, one interviewee recommended expectation management with awareness of developmental stages before, during, and after seed-corn projects.

## What sorts of activities helped to build interdisciplinarity, through what developmental stages?

  - The seed-corn funds facilitated a range of activities amongst applicants at different stages (during the bid-writing process, during the actual project and after the project had been completed).  Such activities, which may have helped to solidify interdisciplinary collaboration and capacity-building between the natural and social sciences, included:

- Informal links and networks between researchers

- Informal links and networks between researchers and other stakeholders

- Cross-disciplinary meetings

- Visits/exchanges of postgrads, postdocs, senior staff between research groups involved in the award

- Cross-disciplinary interactions with stakeholders

- Publications spanning the social and natural sciences

- Subsequent applications to RELU programme

- Subsequent applications to another funder

- Other cross-disciplinary initiatives

- Links between researchers in the award-holders own institution

- Links with other research institutions

  - In terms of indicating some sort of developmental timeframe, the top five activities identified by respondents at each stage were as follows Table 2 (see Annex B for full details):

| Activity | Freq. |
| --- | --- |
| During bid |  |
| Links between researchers | 75% |
| Cross-disciplinary meetings | 45% |
| Links within own institution | 32% |
| Links with other institutions | 32% |
| Links between researchers and stakeholders | 31% |
| During project |  |
| Links between researchers | 86% |
| Links between researchers and stakeholders | 82% |
| Cross-disciplinary meetings | 78% |
| Cross-disciplinary interactions with stakeholders | 60% |
| Links with other institutions | 60% |
| After award |  |
| Interdisciplinary publications | 57% |
| Links between researchers | 54% |
| Links between researchers and stakeholders | 46% |
| Links with other institutions | 46% |
| Further application to RELU (unsuccessful) | 35% |

Table 2: Main activities at each stage of award

  - Responses show a degree of variation when analysed by type of award held (Table 3) although the most popular activities are broadly similar in each case.  Likewise, respondents from different disciplines (environmental science vs. social science) showed minimal variation.

| CBA (N= 16) | SS (N= 34) | DA (N= 9) | NA (N= 8) |
| --- | --- | --- | --- |
| During bid: |
| Links researchers | 81% | Links researchers | 74% | Links researchers | 56% | Links researchers | 100% |
| Cross-disc mtgs | 56% | Cross-disc mtgs | 41% | Links researchers & s/h | 22% | Cross-disc mtgs | 75% |
| Links researchers & s/h | 50% | Links own institution | 29% | Cross-disc mtgs | 22% | Links researchers & s/h | 63% |
| Links own institution | 44% | Links other institution | 26% | Links other institution | 22% | Links own institution | 63% |
| Links other institution | 44% | Links researchers & s/h | 21% | Interactions with s/h | 11% | Links other institution | 63% |
| During project: |
| Links researchers | 94% | Links researchers & s/h | 82% | Links researchers | 100% | Links researchers | 88% |
| Links researchers & s/h | 94% | Links researchers | 79% | Cross-disc mtgs | 89% | Cross-disc mtgs | 88% |
| Interactions with s/h | 88% | Cross-disc mtgs | 74% | Links researchers & s/h | 67% | Links researchers & s/h | 75% |
| Cross-disc mtgs | 81% | Interactions with s/h | 62% | Links other institution | 56% | Links own institution | 75% |
| Links other institution | 81% | Links other institution | 50% | Links own institution | 44% | Links other institution | 75% |
| After project: |
| Links researchers | 81% | ID publications | 62% | Unsuccessful RELU | 67% | Links researchers | 50% |
| Links researchers & s/h | 75% | Links researchers | 44% | Links researchers | 56% | Links researchers & s/h | 50% |
| Links other institution | 75% | Links other institution | 38% | ID publications | 56% | Unsuccessful RELU | 50% |
| Interactions with s/h | 63% | Links researchers & s/h | 35% | Links researchers & s/h | 44% | Links other institution | 50% |
| ID publications | 63% | Links own institution | 35% | Interactions with s/h | 44% | ID publications | 38% |

Table 3: Comparison of most popular activities facilitated by award, broken down by type of award held by respondent

  - When the four types of awards are looked at separately, “linkages across researchers” is clearly the hallmark of the award, cited in first place by all types during the bid process and in either first or second place in the later two stages. Similarly, over all the types of awards, this was identified by three-quarters of respondents for the bid process, 86% for during the project, yet down to 54% after the award, indicating that, naturally, some but not all linkages continue.

  - When looking at the four types of awards, arising from the bid stage, the activity “linkages between researchers and stakeholders” is placed higher during the project (a first place for Scoping Studies, a second and two third places), falling back at the post-award stage. Across awards, the picture is quite clear: links between researchers and stakeholders grew considerably (to 82%) during the project but fall to less than half (46%) afterwards. At 60% during the project across all respondents, when the four types of awards are considered actual “interactions with stakeholders” do not appear during the bid writing stage, and appear only at 3rd and 4th place during the project, and at 4th and 5th place afterwards.

  - After the project, not surprisingly, “cross-disciplinary meetings” fall out of the picture as framed by top rankings. However, two new activities emerge at this stage: Interdisciplinary Publications (cited by over half of the respondents, overall) and Unsuccessful RELU bids.

  - Linkages within a respondent’s own institution decline in importance during and after the project, while linkages with other institutions rose during the project and fell a bit by the last stage, but, in a pattern similar to links with stakeholders, still came in at nearly half of the respondents (46%) as opposed to less than a third (31%) prior to the project, seeming to indicate some lasting success at broadening collaborations.

  - Interestingly, for each activity, Environmental Scientists were “more positive” than Social Scientists (Table 4). One possibility might be that social scientists tend to be more demanding when they consider whether or not to cite processes as effective.

| ES (N= 25) | SS (N= 30) |
| --- | --- |
| During bid: |  |
| Links researchers | 88% | Links researchers | 74% |
| Links researchers & s/h | 48% | Cross-disc mtgs | 41% |
| Links other institution | 48% | Links own institution | 29% |
| Cross-disc mtgs | 44% | Links other institution | 26% |
| Links own institution | 44% | Links researchers & s/h | 21% |
| During project: |  |
| Links researchers | 92% | Links researchers & s/h | 82% |
| Links researchers & s/h | 88% | Links researchers | 79% |
| Cross-disc mtgs | 84% | Cross-disc mtgs | 74% |
| Interactions with s/h | 68% | Interactions with s/h | 62% |
| Links other institution | 64% | Links other institution | 50% |
| After project: |  |
| ID publications | 68% | ID publications | 62% |
| Links researchers | 60% | Links researchers | 44% |
| Links other institution | 56% | Links other institution | 38% |
| Links own institution | 52% | Links researchers & s/h | 35% |
| Links researchers & s/h | 48% | Links own institution | 35% |

Table 4: Comparison of most popular activities facilitated by award, broken down by discipline of respondent

## Did the awards help to forge new linkages and/or strengthen existing ones?

  - The evaluation further sought evidence of any contributions these funding mechanisms had been able to make to enhancing levels of interdisciplinary research capacity.  Of necessity, this evidence often lies in the informed views of those most involved with the mechanisms – those who essentially represent the capacity being developed.

| Respondents agreed that the awards had helped to forge or strengthen linkages between researchers (31% strongly agree; 40% agree; 25% neutral) between institutions (11% strongly agree; 34% agree; 42% neutral) between researchers and stakeholders (17% strongly agree; 43% agree; 31% neutral) but, as these figures show, respondents were more positive about the links between researchers than about cross-institutional links. Moreover, 57% of these collaborations between researchers were in existence prior to the award. |  |
| --- | --- |

  - Award-holders for Capacity Building Awards were generally more positive than others about the beneficial linkages engendered by the award.

| Interestingly, there was a degree of variation in the views of those from the environmental and social sciences. When asked to respond to the statement “Linkages were forged or strengthened between social and natural science disciplines as a result of the award” ES responses: 24% strongly agree; 60% agree; 12% neutral SS responses: 30% strongly agree; 23% agree; 40% neutral |  |
| --- | --- |

## What if any  effects of seed-corn funding persist?

| Looking across all respondents, when asked specifically about the lasting effects, fifty-eight (89%) are still involved in some form of interdisciplinary research between the social and natural sciences following this award and 75% of respondents said that their collaborators in the seed-corn project are also still involved in this type of work (20% of them did not know). Over two-thirds (68%) of respondents are still collaborating with participants from the seed-corn award. While of course there may well be a bias in that those making the effort to respond to the survey may be more likely to still be involved in interdisciplinary work (“the faithful”), these figures do suggest a lasting influence of the seed-corn bids. |  |
| --- | --- |

| More than half agreed that they would be doing their current interdisciplinary work even without the seed-corn award (28% strongly agree; 29% agree; 20% neutral). While this would indicate that the seed-corn award did not necessarily catalyse new interdisciplinary work in all cases, it certainly did so for some. Moreover, it provided individuals already committed to interdisciplinary work with an opportunity to pursue it, with money and credibility. |  |
| --- | --- |

  - Most, if not all interviewees, were positive as to the role of seed-corn grants.  They noted that:

- they encouraged links across disciplines

- engaged people with the interests of RELU and improved development of full projects

- helped in developing new conceptual frameworks, and

- increased learning as to what does and does not work in interdisciplinary efforts.

It was noted that it is inevitably difficult to sort out the exact proportionality of seed-corn activities’ contribution to overall RELU objectives (which were of course also addressed by programme-wide activities and full projects).

| Respondents from both the environmental and social scientists were predominantly neutral on the question of whether a new research community is emerging around the interdisciplinary area addressed by their seed-corn award (total sample 11% strongly agree; 28% agree; 43% neutral). (Some interviewees spoke more in terms of changes in their own personal sense of allegiance to different communities, either RELU broadly or sub-topics under the RELU umbrella.) |  |
| --- | --- |

| However, there was general agreement that the awards had improved respondents’ understanding of other disciplines (18% strongly agree; 57% agree) and, to a lesser extent, familiarity with the research agendas of other Research Councils (11% strongly agree; 49% agree; 31% neutral). |  |
| --- | --- |

  - Survey respondents felt that the greatest benefits they had derived from their experience of the award were (most popular first):

- expertise gained in managing/facilitating interdisciplinary collaborations

- an enhanced ability to cross-fertilise ideas and concepts

- an enhanced ability to frame a problem beyond the confines of any one discipline

- trust-building across participants from different disciplines.

Interviewees described a “ripple effect” as they are invited to

- advise other RELU projects

- receive contacts by prospective colleagues finding them via websites or publications

- give papers in new fora

- spread new paradigms

- publish papers in influential journals

- host international conferences thereby extending networks.

## Has expertise in interdisciplinary working grown?

| Respondents generally agreed that their level of expertise in interdisciplinary working had increased as a result of the award (17% strongly agree; 52% agree; 18% neutral) and almost two-thirds felt that they would be more likely to collaborate across disciplines in the future as a result of the award (22% strongly agree; 40% agree; 23% neutral). On these two points both environmental and social scientists responded in very similar ways. Illustrations of expertise gained are included in Section 3. |  |
| --- | --- |

## Did awards encourage involvement of external stakeholders?

| Almost half of respondents felt that the awards had encouraged more involvement by external stakeholders (14% strongly agree; 35% agree) but 40% of respondents were neutral on this. Award-holders for Capacity Building Awards were generally more positive than others about this, with 75% agreeing or strongly agreeing that the awards had encouraged stakeholder involvement. End-of-award reports cited multiple examples of involvement of stakeholders in activities. Involvement ranged from simple invitations to workshops to core roles in shaping draft proposals, from award-holders disseminating bulletins on research results to genuinely seeking more feedback through deeper consultation. Interviewees also provided a range of comments on issues in stakeholder involvement, with many including stakeholders in workshops, etc. Not all felt that genuine, in-depth stakeholder involvement had been achieved during the short seed-corn grants. |  |
| --- | --- |

## Have seed-corn awards opened up subsequent possibilities for participants?

| A minority of respondents thought that the award had a beneficial impact on their careers (18% strongly agree; 20% agree; 43% neutral). (Some half dozen respondents commented that they felt their RELU award had helped them to get a job.) However, just under half did indicate that they had undertaken one or more new, “professional service” activities as a result of working on their seed-corn project; for example, 22% had been a referee for a Research Council, 23% had been a referee for RELU and 22% had been a referee for an interdisciplinary journal. |  |
| --- | --- |

| Only 20% of respondents felt that the award had helped them to overcome institutionalised barriers to working across disciplines (such as internal administrative procedures or external factors such as the RAE). |  |
| --- | --- |

  - The evaluation also sought to assess whether the awards had strengthened the quality and integration of natural and social sciences in proposals for larger research projects in subsequent calls for funding.  During the course of the award over a third of award-holders had submitted a further successful (15%) or unsuccessful (22%) bid to RELU and following the seed-corn award 15% of respondents had submitted a successful RELU bid, 35% had submitted an unsuccessful RELU bid and 12% had submitted bids to other funders. Of the 163 researchers involved in seed corn projects, 50 eventually participated in full projects (nearly one-third). Those with seed corn experience appeared to have an advantage in subsequent RELU bids: for example, 22% of the 139 seed corn co-investigators were successful in applying at outline stage for the second call of full proposals (compared to only 12% of new entrants and 6% of unsuccessful applicants for earlier seed corn funding). Of the 17 full proposals for the second call, four were funded (nearly 1 in 4), compared to the overall success rate of 1 in 8. Finally, of full proposals for the third call, three of the 12 applications developed from earlier seed corn projects were successful (1 in 4, compared to an overall success rate of 1 in 10). It is too early to assess impact of RELU seed-corn funding on bids to other funders, but it is a positive indicator that such bids are in fact being submitted.

  - Some interviewees noted that the full project RELU bids they submitted were not identical to, or a direct linear progression from, their seed-corn grants.  Interviewees highlighted the benefits interdisciplinary seed-corn teams gained, for example being able to take advantage of a wider range of opportunities but several sounded a cautionary note, fearing that embedded attitudes and reviewing conventions within Research Councils will not be friendly to interdisciplinarity.

| Almost half of respondents felt that the awards had encouraged risk taking in terms of more adventurous research (11% strongly agree; 37% agree). |  |
| --- | --- |

  - Some interviewees expressed concern that reviewers may have leaned toward conventional assessments of quality. Other comments made in interviews, however, highlighted the fact that seed-corn activities were often inherently “risky”, as they often started without teams in place or without having a fully-fledged problem defined for their focus. Some initial ideas proved to be sound; some did not. However, seed-corn grants were seen as often providing opportunities for adventurous research that would not at the outset receive funding as a big project. Furthermore, it would seem that conducting a seed-corn activity could potentially generate evidence of feasibility that would reassure prospective funders of follow-on large projects, with such evidence presumably being particularly desirable if full proposals seem adventurous.

# Lessons Learned & Messages for Future Schemes

## Background information

  - One of the intangible but important contributions made by the seed corn scheme was a particular sort of capacity-building: an increase in expertise in interdisciplinary working. This is, in effect, the development of a resource that will last beyond the scheme.  To help others benefit from this resource, this section draws primarily on insights elicited during interviews, augmented by end-of award reports and free text responses to the survey, and seeks to address the following issues:

- Mobilising a new research community

- Building interdisciplinary research capacity between the natural and social sciences

- Priority issues or obstacles encountered in the pursuit of interdisciplinary research capacity

- Value-added by a particular funding mechanism.

## Mobilising a new research community

  - Trust-building was cited as a key benefit in the survey and interviews: because participants in interdisciplinary teams need to acknowledge what they don’t know, thus displaying vulnerability, trust within a research team is key for capacity-building. Interviews suggested that seed-corn funding was often valuable in mobilising new groupings of researchers – in part but not entirely due to the attractiveness which any new funding opportunity automatically possesses. Working together toward a follow-on bid effectively extends the capacity building process. Face-to-face contact was important: meetings, workshops, travel support all helped people to gain fresh perspectives. Another contribution was the credibility conferred by actually getting a grant, in these RAE-aware times.

  - Many insights had to do with shared understanding of goals. One interviewee emphasised the importance of developing a coalition of the willing, where people really want to work together in an interdisciplinary way, because being forced together doesn’t work. Another has learned that “it requires a very clear understanding amongst individual scientists of their shared set of ambitions for the project… why they want to do the work, as everybody will have different reasons… it is important to have discussions, to say ‘this is why I want to do research; this is what I want to explore’, even if it is difficult to do so”. In similar vein, yet another interviewee spoke feelingly of the need to be very clear about the motivations of your colleagues, when you form an interdisciplinary team, noting difficulties encountered when a previously unknown member of the team appeared to demonstrate interest in the initial grant only as a possible pathway to future money so did not participate in the process of capacity-building. This advice was highlighted in the face of a frequently observed phenomenon --- interdisciplinary work is more difficult and time-consuming than mono-disciplinary research. A preliminary award allows the scope to build the necessary  common commitment.

## Building interdisciplinary research capacity between the natural and social sciences

  - An inevitable aspect of building interdisciplinary research capacity, is the realisation that no one is an expert. Overcoming barriers caused by this discomfort is important when building capacity among researchers who are used to thinking of themselves as experts. For example, an interviewee offered a useful tactic, analogous to involving external stakeholders – making “site visits” to “internal stakeholders” in the various disciplines involved, so that others can learn about each discipline and its approaches. One recommended use of an external advisory board, including some people from other projects, to facilitate learning across projects. Many interviewees reiterated the importance of continuing dialogue and this was also illustrated in end-of-award reports, for example:

“If there is to be integration between scientists and social scientists this should be from an early stage in the research process. This is to ensure that data appropriate for use by all parties is collected. The dialogue between scientists and social scientists should be ongoing, from the involvement of social scientists in the experimental design stages, to the involvement of science in the policy design stages. This is not an easy process but has the potential to prevent some of the difficulties encountered in interdisciplinary working.”

  - Rejecting polarisation as the defining dynamic of interdisciplinarity, a leader of another interdisciplinary programme notes that “understanding the commonalities between the members of an interdisciplinary team is as important, if not more, than becoming aware of their differences”.

  - Stepping back from individual seed-corn grants, the yearly RELU conference and other occasions for interactions between projects were praised. (For example, seed corn leaders often presented work in early conferences and workshops, participated in “linkage maps” illuminating potential for connectivity, and, if selected through peer review, contributed to the special journal issue put together from the first round of RELU projects. However, despite the existence of overlap, there could be additional deliberate mechanisms for following-up across projects, what one interviewee called “some sort of formalised flow”. In at least one case, for example, a PI of a seed-corn award participated in another award; the PI collaborated with the PI of another award to write a joint paper. Similarly, understanding gained, as through Development Awards, could inform the future management of the overall programme.

## Priority issues or obstacles encountered

  - Potentially influencing future endeavours beyond the RELU programme, interviewees were also able to pass along their expertise by identifying certain key messages that illustrate the seed corn scheme’s contributions to interdisciplinary understanding. For example, a tension for funders and for academics allocating their own efforts lies in the relative “value” of bigger grants supporting substantive products that could provide research benefits, versus small seed-corn grants that may cover networking and other such processes that build perhaps less tangible products such as “capacity”. A parallel tension noted for the holders of seed-corn grants was whether they should emphasise processes (such as team-building across the disciplines involved) or try to deliver conventional research outputs.

  - Nonetheless, the very process of working together across disciplines is challenging, with multiple hurdles posed by the necessity of thrashing out differences in language, views, ways of working, approaches to writing papers and so on.

  - Meetings, interactive workshops, informal face-to-face time, regular project meetings, discussion forums, field trips, dialogue, self-evaluation and learning sessions are among mechanisms seen as useful for essential communication, commitment and trust-building.  Key research steps need to be taken together: formulating common research goals, early planning for data management, and continuing cross-referencing as the project proceeds from methods to results. More broadly, as one author of an end-of-award report suggests:

“The key to a more holistic approach, perhaps, is for the project team to collectively develop an appreciation of the methodological rigour that exists at the heart of the research itself, regardless of discipline…. Researchers should strive to make their disciplinary contribution mutually intelligible so that common understandings can be achieved, offering an opportunity for disciplinary research strands to be integrated.”

  - Several lessons were offered regarding stakeholder involvement which may be particularly critical for many interdisciplinary efforts. At least one stakeholder interviewee thinks that the whole purpose of interdisciplinary research is applied research. From the stakeholder viewpoint, at least, a key bit of advice would be that programmes engage with stakeholders, as early as possible, even at the idea and formulation stage, and provide ongoing feedback, otherwise as one researcher acknowledged, “they feel that their contribution has not been valued and they are less inclined to contribute in the future, and furthermore what you do will be of less relevance to them”.

  - Practical lessons offered in end-of-award reports for building relationships with stakeholders included:

- the importance of taking the time to ensure good communication and team-building

- the usefulness of “boundary-spanners” who understand the involved stakeholders in facilitating relationships

- the need for careful planning in organising multi-stakeholder (often controversial) meetings

- the role that small informal meetings - perhaps even site visits - can play in developing a common vocabulary and understanding.

Interestingly, one seed-corn project’s end-of-award report described a deliberate fusion of natural and social sciences for working with stakeholders, an adaptive learning process “designed to engage different disciplines using both qualitative and quantitative methods at different stages of the research process in order to combine the knowledge of natural and social scientists with the knowledge and experience of a wide variety of stakeholders”.

  - An issue that can arise, perhaps particularly for less well-established academics, is that of getting credit for interdisciplinary work in these times of keen RAE-awareness. An important potential obstacle to interdisciplinary work tackling real-world problems is the contrast between the extra time that it takes to conduct and the low value placed on it by many academics. A widely learned lesson is that researchers need to be prepared for this, captured by one interviewee in the following way:

“So, while it is good that policymakers see it as important, so that there are lots of opportunities for funding interdisciplinarity, those researchers who take advantage of the funding promoted by policymakers also have to be prepared to accept that their work may be regarded by many as being of less quality, by virtue of being interdisciplinary. Often, interdisciplinary work may be published in what are seen as lesser journals, often tackling real-world problems rather than theory.”

  - Since forewarned is forearmed, generic challenges identified from end-of-award reports are captured here for the benefit of others undertaking interdisciplinary work in the future.

- the time (and energy)-consuming nature of interdisciplinary work

- discomfort caused by embedded differences in approach, e.g. to complexity, or in priorities as to the most important research questions

- personal barriers, such as conflicts with being a recognised “expert” in one discipline

- practical barriers including different  literature, accessibility of data

- institutional barriers such as personnel or budgetary management

- differences in spatial and temporal scales used by different disciplines, and by stakeholders

- language including “the epistemological and ontological assumptions” behind the words.

- Need for techniques to integrate data from across disciplines

- Career prospects

- Competition with mono-disciplinary research

- Recruitment and retention of staff for small, short-term projects.

  - In free text responses, when survey respondents described “the most important lesson learnt” through their seed-corn activity: by far the most prominent lesson had to do with the extensive time required to build interdisciplinary communities (often including stakeholders) (Table 5). Many stressed the importance of continuity and momentum, for trust relationships and for staff, such that follow-on funding, or longer periods of seed-corn funding, were desired. Clarity, and commonality, of purpose were seen as important, so much so that several recommended working with people already known to each other. Several respondents suggested key steps, such as maintaining dialogue or managing data, while several others stated firmly the importance of selecting and/or training reviewers to assess interdisciplinary bids fairly and appropriately.  Understanding of interdisciplinary processes was seen as a good thing, along with appreciation for obstacles and all-too-frequent “irrelevance” of interdisciplinarity to career progression. Some stated accomplishments of the seed-corn grants, e.g. “they work well, generate research output in their own right, and reduce the risks and transaction costs for subsequent major bids”.

| Lesson | Freq. |
| --- | --- |
| Interdisciplinary research takes more time | 10 |
| Importance of follow-on £, activity | 8 |
| Clarity of purpose, knowing team members | 5, 3 |
| Process, steps | 6 |
| Assessment appropriate to interdisciplinary bids | 6 |
| Knowledge of interdisciplinarity | 4 |
| Obstacles | 3 |
| Accomplishments, Coverage | 3 |
| Unrecognised value in career | 2 |

Table 5: Topic distribution of lessons learned cited by survey respondents

  - On occasion, some issues were raised regarding the management and, in particular, the assessment of the funding awards. One interviewee expressed disappointment that, in their view, there had not been more risk-taking in the awarding of the small grants of course, at some level, risk-taking may be integral to any interdisciplinary endeavour. A perhaps related comment about the level of caution among assessors came in the complaint of a stakeholder interviewee, familiar with the bid assessment process, when bids that were to him “obviously” useful research were often discounted by academic reviewers as not sufficiently cutting-edge in the various disciplines involved.

  - Some felt that the RELU assessment process should properly give extra weight to interdisciplinary ambition in bids for seed-corn projects and/or follow-on full project bids (e.g. awarding “points” to those showing that a strong interdisciplinary potential exists, ideally showing proof of interaction or some level of contact). As an example, one interviewee with experience in reviewing bids for RELU observed that the really good proposals had some equality of intellectual input between the natural and social sciences, rather than one arena being just an add-on. Assessment of interdisciplinary bids is an intrinsically contentious issue. Whatever the criteria, their clear communication is of course important.

  - In terms of practical aspects of managing the seed-corn grants, a mis-match was perceived between Research Councils’ wish to allocate the money to a set schedule, and the extra time required for the process of building interdisciplinary teams. Several end-of-award reports described the pressures in preparing applications for full projects while at the same time running the seed-corn project,.  One researcher interviewee noted that the sudden need to hurry and write a full project proposal necessitated deepening relationships among just a handful of team members rather than building up a broad capacity across wider communities over a longer period of time, as originally planned. Some processes, e.g. notification of awards and processing of contracts, were sometimes felt to be slower than would be optimal. The length of a seed-corn grant may have implications for recruitment and retention of individuals (and vice versa, for short-term projects).

  - There was a sense that funders or leaders of initiatives/schemes could contribute advice on key processes (such as building trust, developing interdisciplinary relationships) to make seed-corn projects more successful, in other words disseminating lessons such as those learned through the RELU seed-corn scheme to wider audiences.

## Value-added

  - Survey responses across the four award types are generally quite similar, suggesting not much differentiation between the different mechanisms in terms of outputs or value-added. Relatively few interviewees made fine-tuned distinctions between the four types of seed-corn funding (of course, most were only involved directly with one or at most two types).  On the other hand, one PI interviewee particularly praised RELU’s approach of providing a portfolio of different types of seed-corn funding.  However, while also raising the usefulness of having different modalities, another interviewee did suggest that this was sometimes confusing. One interviewee made the distinction between a capacity building grant, oriented toward processes of people learning from each other at workshops and presentations, and a scoping grant, of necessity very problem-focused on developing a research project (and bid) for later funding and thus deferring the ability to help people really interact via an integrated model. Another described the limit in team size natural to a development award and its small funding, making them more like think pieces rather than proto-team developing activities.  Finally, one interviewee with a broad perspective viewed the networking awards as least successful, receiving very low funding and infrequently gaining follow-on grants – often the furthest away from being able to involve people, help them work together and put in a competent bid.

## Other seed-corn programmes

  - Interviews with senior figures in other programmes, as well as with RELU-related interviewees aware of other programmes, elicited insights as to seed-corn mechanisms generally. RELU appears to sit comfortably within the range of activities and levels of funding (although some of its awards are at the small end of the spectrum). Different programmes may use different names, e.g. “cluster grants” bringing together new clusters of researchers, but they share with RELU what seem to be key seed-corn objectives: promotion of capacity to conduct interdisciplinary research, catalysis of research linkages and collaborations, generation of a greater critical mass of researchers tackling key issues, (often) involvement of stakeholders and encouragement of risk-taking.

  - There is a strong sense among other programme leaders that the experience of having had seed-corn funds strengthens researchers’ proposals for full projects. One programme leader observed for example that two-thirds of their phase two grants are led by individuals who were either PIs or participants in their phase one (seed-corn) grants. There is a sense that seed-corn awards may limit risk, by taking the risks when funding is relatively low, prior to full-stage funding. There is also a hope that even seed-corn experience will give researchers advantages in other competitions, such as EU funding, when relationship-building is required.

## Messages for future seed-corn funding schemes

  - As with the accumulation of lessons learned that can be utilised by others undertaking diverse seed-corn interdisciplinary research projects in the future, the RELU seed-corn funding scheme also gave rise to useful messages for others funding or leading seed-corn schemes in the future. This is another form of capacity-building by RELU. Perhaps the most important message is that 91% of all survey respondents, and a similar proportion of interviewees, would recommend seed-corn funding as a means of building interdisciplinary capacity (and this figure was fairly consistent across disciplines, role, award type and whether or not the respondent was still working in an interdisciplinary environment). Clearly seed-corn funding is regarded as an important catalyst for interdisciplinarity. However, many qualified their comments by articulating what they saw to be appropriate objectives or essential features of a seed-corn grant scheme; offering suggestions for improved delivery of seed-corn grant schemes; discussing issues or emphasising the broader context within which seed-corn grants would have to sit to be effective. Highlights of suggestions stemming from these comments follow.

  - Clearly, just as researchers can benefit from a reservoir of lessons learned by other researchers attempting interdisciplinarity, so can funding bodies learn from each other’s experiences in other seed-corn schemes. For example, if several funding bodies are involved, they should expect to take more time than for a conventional mono-disciplinary programme to design a joint seed-corn scheme, define common objectives and expend more energy streamlining administrative burdens. In fact, a senior figure of another programme indicated that their programme learned from RELU’s funding scheme and consequently spent more time getting all the funding partners on board and jointly designing the programme. And in turn, the early design of the RELU seed-corn scheme had apparently been influenced by NERC’s small proof of concept grants for larger consortium grants.

  - Some other recommendations pertained to:

- effective management of seed-corn funding schemes; for example: design schemes to meet clearly defined objectives

- communicating criteria clearly in calls for proposals

- helping researchers to meet and share ideas and good practice across projects;

- allowing sufficient time for seed-corn projects to conduct time-consuming processes such as relationship-building or development of a common language (for example, waiting before calling for full project proposals).

  - Other key roles recommended for leaders of initiatives or schemes were communication to researchers as to the importance of processes in the seed-corn stage and provision of advice or sharing of lessons learned as to good practice in those processes (such as lessons learned through RELU). Formative evaluation during a scheme was recommended, and would contribute to these roles.

  - Assessment appears frequently as a critical issue in the catalysis of interdisciplinarity. Future funders and leaders of schemes are encouraged to:

- develop appropriate assessment processes

- use criteria and weighting that suit interdisciplinarity

- select or train assessors who understand interdisciplinarity.

  - Including assessors who understand the importance of interdisciplinarity-building, and helping other assessors to learn about such processes, will sensitise assessment procedures to telling indicators of likely success, whether in awarding seed-corn funds or follow-on funding. So, for example, as the RELU programme moved on, assessment panel  members became more experienced, systematic efforts were made to familiarise them with the nature of interdisciplinary goals for projects and assessment panels were specifically directed to make distinct assessments of the interdisciplinary ambition of proposed projects.

  - Funders were challenged to think through the prospects for researchers on risk-taking seed-corn projects, both in terms of immediate possibilities for full project funding and also, more systemically, in terms of improving funding and related career trajectories for interdisciplinary researchers.

# Conclusions

## Summary of findings

  - The awards did mobilise interest in the RELU programme and its issues from across the social, environmental and biological sciences. The prospect of gaining seed-corn awards successfully stimulated interest and potential engagement, with researchers often finding this to be an opportunity to address a pent-up desire to do interdisciplinary work and/or to tackle problems of particular interest to them. Environmental scientists were slightly more positive about this mobilising effect than were social scientists.

  - The awards have enhanced levels of interdisciplinary research capacity. Researchers have participated in interdisciplinary work and have learned lessons about processes involved. Effectively the hallmark of the award, linkages have been forged or strengthened between researchers and between disciplines, very often building on earlier relationships. To a lesser extent, linkages were formed with stakeholders.

  - At various stages (pre-award or bid-writing, award, post-award), a variety of “linking” activities were facilitated by the awards, ranging from informal networks to workshops to publications and follow-on proposals.

  - There appear to have been lasting effects of the linkages forged: almost ninety per cent of the survey respondents are still involved in interdisciplinary research spanning social and natural scientists, with most believing that their collaborators also continue to do this sort of work.  The awards seemed to lead toward somewhat more favourable attitudes toward interdisciplinary collaboration, although many if not most of the researchers entering into the seed-corn projects were already favourably inclined.

  - Some linkages have been forged or strengthened with stakeholders and across institutions, with some of these linkages remaining more intense than prior to the awards.

  - A variety of opportunities and/or subsequent activities were facilitated, primarily in the form of interdisciplinary publications and continuing research linkages, with some joint proposals being written to RELU and elsewhere, while lasting institutionalised links did not appear to be as frequent.  It may well be that future interdisciplinary bids may benefit from lessons learned about processes as well as from building of specific relationships within a team.   Although some participants saw the experience as contributing to their securing of subsequent positions, many raised concerns over the general issue of lack of career progression prospects for interdisciplinary researchers. Other lasting effects include the increased ability of seed-corn researchers to participate in interdisciplinary collaborations in the future. This practical learning among a cadre of researchers represents a national resource to which the RELU seed-corn scheme has contributed. “Lessons learned” presented in this Review illustrate this growth in understanding as to the processes through which interdisciplinary research can be developed and optimised.

  - Quite practical lessons were learned regarding the building of interdisciplinary capacity in the future. This enhancement of understanding represents a contribution by the RELU seed-corn scheme to the future of both individual researchers’ efforts and also. Examples of  overarching lessons regarding the building of interdisciplinary research capacity between the natural and social sciences, and the mobilisation of a new research community include:

- length of time and degree of effort needed

- the importance of prospects for follow-on activity and funding

- the importance of clear, shared objectives

- the need to understand necessary processes and steps

- the identification of a number of issues and challenges arising during interdisciplinary research.

  - In terms of the four different seed-corn funding mechanisms, the nature and impacts of capacity building and scoping awards were not readily distinguishable.  Development awards appeared to perform a useful service by informing the programme overall about interdisciplinarity per se, along with related questions. Networking awards appeared to have by far the least lasting impact, perhaps as they were very short-term and very modestly funded, without, it seemed, the degree of focus possessed by the other mechanisms.  Results suggest that the division into four mechanisms seemed unnecessary. Rather, it might be preferable to offer one more generalised, flexible scheme of seed-corn awards, which could be clearly defined to encompass the several types of nature/aim, rather than to artificially “force” distinctions among different award streams.

  - RELU’s funding mechanisms appear effective, in a general comparison with those used in other interdisciplinary programmes (although of course these other programmes were not reviewed in comparable detail). Some administrative aspects could have been improved, primarily the speed with which calls and awards were announced and, especially, the timing of calls for full proposals relative to very young seed-corn projects. Issues of assessment appropriate to interdisciplinary bids (e.g. those following after seed-corn projects) also arose. Some other programmes appear to make a point of bringing together their seed-corn counterparts to share concerns and good practice as to processes involved; some may give their seed-corn projects a somewhat higher profile within their overarching initiative, although RELU’s seed-corn projects were highly visible in the programme’s early years. Most seed-corn schemes, like RELU’s, aimed for both enriched understanding of complex issues and development of effective interdisciplinary teams and ways of working.

  - Another contribution made by RELU’s pioneering work lies in a number of lessons learned that were offered as suggestions to funders or leaders of seed-corn schemes in future research programmes on complex topics. Some were analogous to messages to seed-corn project leaders, e.g. take the extra time needed to design and establish the scheme and capture and share lessons learned across funding bodies, as well as across researchers. Assessment issues were raised, particularly the need to select or train assessors who can place appropriate value on proposals showing genuine interdisciplinarity, thus allowing seed-corn projects that have achieved this aim to be successful in follow-on funding. In the broadest picture, funders were encouraged to consider future funding and career prospects for those participating in interdisciplinary seed-corn projects.

## Reviewers’ final comments

  - In summary, the Reviewers found RELU’s seed-corn scheme to be effective in addressing its aims. While the data gathered from our survey of award-holders are almost entirely positive, the more nuanced understanding provided by the interviews does, however, hint at a slight regret that stakeholders had not been more intimately involved and that assessment processes were not always sufficiently attuned to interdisciplinary risk-taking, coupled with a rather elusive sense that, somehow, hopes for the scheme had been just a bit higher. (This may be accounted for at least in part by the foreshortening that occurred when many seed-corn award-holders had to rush into writing full-project proposals.) However, the RELU seed-corn scheme was certainly sufficiently successful to demonstrate that seed-corn funding can play very important roles in catalysing interdisciplinarity and the building of capacity and communities to tackle tough problems.

  - Not only did the seed-corn scheme contribute to the RELU programme, in doing so it also contributed to broader interdisciplinary capacity in its field.  Seed-corn researchers have in many cases increased their commitment to and/or competence at interdisciplinary working – they thus represent a resource for interdisciplinary work of the future. (Indeed they, and others associated with RELU, will in many cases be better able not only to publish “respectable” interdisciplinary articles but also to assess interdisciplinary proposals, functions critical to the growth of interdisciplinarity practice and capacity.)

  - Lessons learned through the RELU seed-corn experience indicate that it is indeed possible for researchers conducting seed-corn projects to become more successful at building interdisciplinary skills and community, if they come to understand the processes involved. (Such processes are illustrated, for example, by this Review’s explication of the flow of activities dominating the various stages of bid-writing, conducting the award, post-award.) There is a general appetite for this sort of learning, such that sharing it could help to avoid reinvention of wheels and unnecessary problems in pursuing seed-corn projects.  Similarly, funders of the future can learn from others’ experiences with seed-corn schemes, for example the challenges of managing assessment for interdisciplinary proposals, so that they contribute effectively to desired impacts. We hope that this Review of RELU’s seed-corn scheme will contribute to both these reservoirs of organisational learning.

# Footnotes

We subsequently omitted from our reminders all those who were associated with the Networking Awards, other than their PIs, as several people in this category contacted us to say that they had no recollection of these awards.  In addition, two further names were removed from the database where people were on sick leave or fieldwork overseas.

Percentage figures quoted are based on the number of respondents returning a completed survey, not on the number answering a particular question, as the majority of respondents answered every question.

This figure is low in part because there was an open RELU call on the sustainable food chain at the same time as the seed corn mechanisms were advertised and this larger call attracted more applicants from the biosciences.

Statistics on success rates provided by Jeremy Phillipson, Assistant Director, RELU

Rural Economy and Land Use: The Scoping of an Interdisciplinary Research Agenda, Special Issue of the Journal of Agricultural Economics 57 (2)

It is worth remembering that several individuals who were sent the survey declined to complete it on the grounds that they did not remember participating in a networking award (see footnote 1).

# Text boxes

2%

Other

14%

RA

46%

Co-I

38%

PI